## Sheet1
Sprint backlog
Media Player |  |  | Month | September | [7 empty] | October
|  |  | Week | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5
|  |  | Days | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23
# | 1st Sprint Tasks | days | Progress
1 | Making an interface | 13 | bar: 2020-10-01 to 2020-10-13
Estimated time | bar: 2020-10-01 to 2020-10-13
2 | Add a control section with buttons that are demanded | 3 | bar: 2020-10-02 to 2020-10-04
3 | Write function for pause/un-pause of music | 3 | bar: 2020-10-03 to 2020-10-05
4 | Write function for changing to next/previous music | 2 | [32 empty] | Actual time | bar: 2020-10-04 to 2020-10-05
5 | Write function for increasing/decreasing volume | 2 | bar: 2020-10-05 to 2020-10-06
6 | Write function for repeat option | 2 | bar: 2020-10-06 to 2020-10-07
7 | Write function for repeat option for one sound track | 2 | bar: 2020-10-08 to 2020-10-09
8 | Write function for a timer to measure the length of music | 2 | bar: 2020-10-10 to 2020-10-11
9 | Being able to play sound tracks | 10 | bar: 2020-10-05 to 2020-10-13
10 | Supporting different types of files (MP3, WAV, WMA, M4A...) | 8 | bar: 2020-10-07 to 2020-10-13