## Sheet1
PRODUCT BACKLOG
Story ID | Priority | As a <type of user> | I want to <perform a task> | So that I <can achieve a goal> | Status
1 | High | Product owner | have my software to capable of playing media files (video and audio) | can use it to play media files | In progress
2 | High | Product owner | have an interface for my software | work easily with it | In progress
3 | Medium | User | be able to pause/un-pause | could pause it when I need to, then un-pause and continue it | In progress
4 | Medium | User | be able to change to next/previous media file | can skip to another song | In progress
5 | High | User | see all my media files in a list | can easily select one from there | Not started
6 | High | Product owner | have a control section | control the file from there | In progress
7 | Medium | Product owner | increase and decrease the volume | can adjust it to my level of liking | In progress
8 | Medium | User | have a repeat option | see/listen to my list without manually re-starting it | In progress
9 | Medium | User | have a repeat option that only repeats one song | see/listen to one file that I want | In progress
10 | High | Product owner | be able to create playlists | can see/listen only to a group of media files | Not started
11 | Medium | User | add/remove songs from a playlist | do not have to remake a list every time I want to bring any changes | Not started
12 | Low | User | be able to name/rename a playlist | identify/differentiate between list easier | Not started
13 | Medium | Product owner | have a software that can support different types of files (MP3, MP4...) | do not have to make/use another media player | In progress
14 | Low | User | have a timer to show the length of the media file | can know how long it is | In progress